## Guide
Sprint 1 (viikon mittainen)
Maanantai | Tiistai | Keskiviikko | Torstai | Perjantai | Pidetäänkö 15 min daily scrum päivittäin samaan aikaan?
Sprint planning meeting |  |  |  | Sprint Review & Sprint Retrospective

## ProductBacklog
Group 4
| Product Backlog - Vaalikone | [5 empty] | Priorities |  |  | Product Backlog? | Story Points
Number | User Story | Story Point(s) | Priority |  | low (could) |  | medium (should) |  | high (must) | Reprioritized at the start of each sprint | 1= easy
1 | As a voter, I should be able to answer the questions. | 4 | 5 |  | 1 | 2 | 3 | 4 | 5 | Contains all desired work to be done | 2 = 2 x easy
2 | As a voter, I want to be able to see the best candidate for me. | 8 | 5 | [7 empty] | 16 = 16 x easy
3 | As a voter, I am able to compare my answers to the candidates' answers. | 4 | 4
4 | As a voter, I am able to see information of the 2nd candidate and 3rd etc. (How many?) | 3 | 3
5 | As a user, I should be able to see all the candidates, even before I answer the questions. | 2 | 2
6 | As a user, I want to be able to sort the candidates in alphabetical, best for me or party order. | 1 | 1
7 | As an admin, I should be able to log in. | 1 | 1
8 | As an admin, I should be able to add, read, edit and remove candidates. | 8 | 4
9 | As an admin, I should be able to add, read, edit and remove election machine questions. | 8 | 4
10 | As an admin, I should be able to add, read, edit and remove candidates' answers. | 4 | 2
11 | As an admin, I want to be able to search for questions. |  | 2
12 | As a candidate, I should be able to answer the questions and edit my answers. | 4 | 5
13 | As a candidate, I should be able to explain my answers | 3 | 3
Plussaa saa
DAO
PreparedStatement (Tietokanta)

## Sprint_backlog_sprint1
Sprint Backlog : Sprint 1 (28.3. - 3.4.2022)
Backlog Task & ID | Story Points | Assigned to | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Goal of the sprint (Vapaaehtoinen)
Not user story |  |  |  | Hours to do task
Set up GitHub | 1 | Erik | DONE | 0.5 | 0.1 | - | - | -
Tietokannan sisällön luominen | 3 | Toni | DONE | 2 |  | 0.5 | 2
Design user interface for website | 1 | Everyone | DONE | 1 |  |  | 1
JSP
User story: As a voter, I should be able to answer the questions. | [10 empty] | MVC
Questions in database | 1 | Everyone | DONE 3/3
Being able to see questions (CRUD, R) |  | Erik & Toni | DONE | 2 | 3 | [5 empty] | Plussaa saa
User interface |  | Janette | DONE? | [7 empty] | DAO
User is able to answer the questions | 1 | Toni | DONE |  | 1 | [5 empty] | PreparedStatement (Tietokanta)
Answers go somewhere? Database? List? | 2 | Toni | DONE? |  | 3
DAO |  | Everyone
As a voter, I want to be able to see the best candidates to me.
Getting candidates answers from DB |  | Janette | DONE? |  |  |  |  | 1
Comparing the answers | 3 | Toni | DONE |  |  |  |  | 5
Candidates to order |  | Toni??
Showing candidates information |  | Janette | DONE
Getting candidates pictures from DB (From folder instead) |  | Erik | DONE |  |  |  | 5
As a user, I should be able to see all the candidates, even before I answer the questions.
Create User interface for "All candidate page" |  | Erik & Janette | DONE
Every candidate has his/her own page |  | Erik | Done Sprint 2
See more info about candidate |  | Erik | Done Sprint 2
Getting candidates information from DB to "All candidate page" |  | Janette | DONE |  |  |  | 4
Getting candidates information from DB to "Certain candidate page" |  | Toni | DONE
Total |  |  |  | 5.5 | 7.1 | 0.5 | 12 | 6

## Sprint_backlog_sprint 2
Sprint Backlog : Sprint 2 (4.4. - 10.4.2022)
Backlog Task & ID | Story Points | Assigned to | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Goal of the sprint (Vapaaehtoinen)
Not user story |  |  |  | Hours to do task
Whole websites user interface to look nice | 3 | Everyone |  | 3 |  |  |  | -
As an admin, I should be able to add, read, edit and remove candidates. | 8
Edit candidate |  | Toni | DONE | [7 empty] | JSP
Remove candidate |  | Toni | DONE | [7 empty] | MVC
Read candidate |  | Toni | DONE
Add candidate | 5 | Toni & Janette | DONE |  | 2 |  | 3 |  |  |  | Plussaa saa
DAO
PreparedStatement (Tietokanta)
As an admin, I should be able to add, read, edit and remove election machine questions. | 8 | [9 empty] | All user storys
Add questions |  | Janette | Penan kurssilla | [7 empty] | As a voter, I should be able to answer the questions. | 4
Read questions |  | Janette | Penan kurssilla | [7 empty] | As a voter, I want to be able to see the best candidate for me. | 8
Edit questions |  | Janette | Penan kurssilla | [7 empty] | As a voter, I am able to compare my answers to the candidates' answers. | 4
Remove questions |  | Janette | Penan kurssilla | [7 empty] | As a voter, I am able to see information of the 2nd candidate and 3rd etc. (How many?) | 3
User interface (html & css) |  | Everyone | Penan kurssilla | [7 empty] | As a user, I should be able to see all the candidates, even before I answer the questions. | 2
[11 empty] | As a user, I want to be able to sort the candidates in alphabetical, best for me or party order. | 1
As an admin, I should be able to log in. | 1 | [9 empty] | As an admin, I should be able to log in. | 1
User interface (html & css) |  | Everyone | Penan kurssilla | [7 empty] | As an admin, I should be able to add, read, edit and remove candidates. | 8
login stuff |  | Janette | Penan kurssilla | [7 empty] | As an admin, I should be able to add, read, edit and remove election machine questions. | 8
[11 empty] | As an admin, I should be able to add, read, edit and remove candidates' answers. | 4
As an admin, I want to be able to search for questions.
As a voter, I am able to compare my answers to the candidates' answers. | 4
Display on JSP page after answering from questions page |  | Erik | DONE | 5 | [6 empty] | As a candidate, I should be able to answer the questions and edit my answers. | 4
Display in order on JSP page | 5 | Toni | DONE | 2 |  | 1 | 2 |  |  |  | As a candidate, I should be able to explain my answers | 3
Button on page to show more possible candidates |  | Janette
User interface (html & css) |  | Everyone
I am able to see information of the 2nd candidate and 3rd etc.
As an admin, I should be able to add, read, edit and remove candidates' answers.
Add answers |  | Erik | Penan kurssilla
Read answers |  | Erik | Penan kurssilla
Edit answers |  | Erik | Penan kurssilla
Remove answers |  | Erik | Penan kurssilla
User interface (html & css) |  | Everyone | Penan kurssilla
As a user, I should be able to see all the candidates, even before I answer the questions. (From last week)
Every candidate has his/her own page |  | Erik | DONE | 2 | 2 |  | 1 | 1
Display how the candidate has answered the questions |  | Erik | DONE | [5 empty] | 1 | 6
Total |  |  |  | 12 | 4 | 1 | 6 | 1 | 1 | 6
Note on D17: Day 2 on sprint: We got so much done on first week that we don't need to do most of the user stories we planned for this 2nd sprint.

## Sprint_backlog_sprint3
Sprint Backlog : Sprint 3 (11.4.-17.4.2022)
Backlog Task & ID | Story Points | Assigned to | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Goal of the sprint (Vapaaehtoinen)
Not user story |  |  |  | Hours to do task
Whole websites user interface to look nice | 3 | Everyone |  | 3 |  |  |  | -
As an admin, I should be able to add, read, edit and remove election machine questions. | 8 | [9 empty] | Penan kriteerit?
Add questions | [10 empty] | JSP
Read questions | [10 empty] | MVC
Edit questions
Remove questions | [10 empty] | Plussaa saa
User interface (html & css) |  | Everyone | [8 empty] | DAO
PreparedStatement (Tietokanta)
As an admin, I should be able to add, read, edit and remove candidates' answers. | [10 empty] | All user storys
Add answers | [10 empty] | As a voter, I should be able to answer the questions. | 4
Read answers | [10 empty] | As a voter, I want to be able to see the best candidate for me. | 8
Edit answers | [10 empty] | As a voter, I am able to compare my answers to the candidates' answers. | 4
Remove answers | [10 empty] | As a voter, I am able to see information of the 2nd candidate and 3rd etc. (How many?) | 3
User interface (html & css) |  | Everyone | [8 empty] | As a user, I should be able to see all the candidates, even before I answer the questions. | 2
[11 empty] | As a user, I want to be able to sort the candidates in alphabetical, best for me or party order. | 1
As an admin, I should be able to log in. | 1 | [9 empty] | As an admin, I should be able to log in. | 1
User interface (html & css) |  | Everyone | [8 empty] | As an admin, I should be able to add, read, edit and remove candidates. | 8
login stuff |  | Janette | [8 empty] | As an admin, I should be able to add, read, edit and remove election machine questions. | 8
[11 empty] | As an admin, I should be able to add, read, edit and remove candidates' answers. | 4
As an admin, I want to be able to search for questions.
[11 empty] | As a candidate, I should be able to answer the questions and edit my answers. | 4
[11 empty] | As a candidate, I should be able to explain my answers | 3
Total |  |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint_planning_meetings
Sprint Planning | Participants
Week 1 (28.3. - 3.4.2022) | Janette Lehto | Toni Nurmi | Erik Kihn
Online | Online | Online | Online
Date done: 22.3.2022
What needs to be done:
How will it be done:
Week 2 (4.4. - 10.4.2022) | Janette Lehto | Toni Nurmi | Erik Kihn
Online | Online | Online | Online
Date done: 4.4.2022
What needs to be done:
How will it be done:
Week 3 | Janette Lehto | Toni Nurmi | Erik Kihn
Online
Date:
What needs to be done:
How will it be done:
Note on A6: Deepak haluaa nähdä vain mitä backlogeisssa on ja ketä on osallistunut kokouksiin

## Sprint Reviews & Sprint Retrosp
Sprint Review & Restrospective |  |  |  |  | What is Sprint Review?
Sprint 1 (28.3. - 3.4.2022) | Date: 4.4.2022 |  | Sprint Retrospective |  | What has been accomplished during the sprint?
What we were supposed to do | What we were able to do | What we were not able to do | What is not working? | What is working? | 2h prep time for Sprint review (hmmm)
DAO, data, JSP | DAO, data, JSP | User interface to top standard | - | Everything so far | No slider, no PowerPoint
|  | Single candidate |  |  | Whole team participates
Best candidate is not displayed
Janette Lehto | Toni Nurmi | Erik Kihn |  |  | What is Sprint Retrospective?
Online | Online | Online |  |  | 15- 30 min
What is not working?
What is working?
Sprint 2(4.4. - 10.4.2022) | Date: 11.4.2022 |  | Sprint Retrospective |  | Whole team participates
What we were supposed to do | What we were able to do | What we were not able to do | What is not working? | What is working?
Pages for single candidates | Finish up work |  | Should be more testing of code
Add candidates
Janette Lehto | Toni Nurmi | Erik Kihn
Online | Online | Online
Sprint 3 (Week 3) | Date: |  | Sprint Retrospective
What we were supposed to do | What we were able to do | What we were not able to do | What is not working? | What is working?

## Tietokanta taulut, SQL
Karkea idea miltä taulut näyttäisi |  |  |  | Alleviivatut on primare keytä
| Candidate | NOT NULL |  |  | NOT NULL |  |  |  | NOT NULL |  | Admin tunnuksien taulu
| ID | Surname | First name | Age | Party | Profession | Why are you here? | What do you want? | Vote # | ID | Nimi | Salasana
| 1 | Duck | Donald | 36 | Socialist | Kumileipä | In my opinion the amount of work an anthropomorphic animal has to do just to live their life normally is way too much. | Something to occupy my feeble mind while I try to avoid working as much as I can. | 313 | 1 | Admin | 1234
| 2 | McDuck | Scrooge | 75 | Indepentend | Business magnate | I need money | Money | 112
| 3 | Gander | Gladstone | 38 | Republican | - | I just take part of every competition I can find, I'm so lucky that if I win, I win, and if I lose, I know I dodged a bullet, so it's always a win-win situation for me. | It doesn't matter if I win, as long as Donald (Duck) loses. | 777
| 4 | Duck | Daisy | 35 | Enviromentalist | TV reporter | Someone needs to do something about the flowers in the middle of the park, they are dying! | My promise is to fix the flowers and then I'll probably resign. | 666
| 5 | Gearloose | Gyro | 50 | Libertarian | Inventor | My inventions will bring a new brighter future for everyone in Duckburg. | To make the living conditions of your every day citizens easier and more stress free. To automate most of the working places, so that people can roam free daily without selling their souls to faceless corporations. | 314
| 6 | Mouse | Mickey | 47 | Socialist | Jack-of-all-trades | I am the most reliable person you will ever meet! | I want to be part of recreating the glory of Duckburg that I remember we had when I was just a wee lad. | 420
| 7 | Mouse | Minnie | 47 | Republican | Barmaid | I feel like no one else gets things done. No one gets things done better than I do, go ask anyone. Ask me for example. | Make Duckburg Great Again | 137
| 8 | Pluto |  | 8 | Anarchist | Dog | Woof | Woof woof | 100
| 9 | Duck | Huey, Dewey and Louie | 11 | Pirate party | 3 children in a trenchcoat | We... I mean, I feel like schools give too much homework for us... I mean, the children, and also recess is way too short, it should be over 1 hour long. | Free candy for every children in Duckburg and never having to go to school again! | 333 |  |  |  | Saako olla null arvoja missänä taulun arvoissa? | Yhteydet taulujen välillä?
| 10 | Goof | G.G. "Goofy" | 61 | Socialist | Comedian | Why is anyone anywhere? What is the point of life? Are we all just puppets here for the entertainment of some greater intergalactic cosmic beign that plays with the lives and minds of the innocent? What was the question? | I don't know, PlayStation 5 or something. | 123 |  |  |  | Perusvain (Primary key , ID?)
Viiteavain
| Answers |  | NOT NULL |  |  |  | Questions | NOT NULL
| Answer ID | Candidate ID (foreign key) | Question ID (foreign key) | Answer (Integer) | Answer (String) |  | ID | Question
[7 empty] | 1 | Duckburg, Mouseville and Goosetown should all be combined into one big city.
[7 empty] | 2 | The roads of Duckburg are in good condition.
[7 empty] | 3 | The city of Duckburg should add more public transportation options.
[7 empty] | 4 | Duckburg needs more car repair shops. |  |  |  |  | Esimerkki
[7 empty] | 5 | SAMPLE TEXT
[7 empty] | 6 | Fethry Duck is a menace to society.
[7 empty] | 7 | Schools should adapt more to the distance education model.
[7 empty] | 8 | We live in a society.
[7 empty] | 9 | Scrooge McDuck's Money Bin should be moved away from Duckburg.
[7 empty] | 10 | I don't agree with this statement.
[7 empty] | 11 | Somebody once told me the world is gonna roll me.
[7 empty] | 12 | Duckburg has too many ducks.
[7 empty] | 13 | Every job in Duckburg should be automated.
[7 empty] | 14 | The ducks and other birdlike citizens of Duckberg should be able to fly.
[7 empty] | 15 | Dark chocolate is better than white chocolate.
Sarakkeiden määrittäminen
Note on N4: Hashed muodossa??